## Sheet1
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
1RsLp82KlsdQp11 | Prepare UI wireframes for student risk dashboard and explainability panel | Design | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2025-03-12 | 2025-03-12 | 812/2025 | FALSE | FALSE | 2025-10-12 | RAVISANKA U V P it22354792 |  |  | Yellow | UI wireframes for risk dashboard
T2bLx83LmpsQz12 | Prepare UI wireframes for student dashboard | Design | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2025-03-12 | 2025-03-12 | 2025-08-12 | FALSE | FALSE | 2025-08-12 | DISANAYAKA S T it22370228 |  |  | Yellow | Create initial UI layouts for dashboard
8LkWk92PdskQp11 | Prepare UI wireframes for chatbot interface | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2025-04-12 | 2025-04-12 | 2025-09-12 | FALSE | FALSE | 2025-09-12 | NIMANJI D L K it22365750 |  |  | Yellow | Design chatbot UI layout
T1aXk92DkslQp01 | Prepare UI wireframes for chatbot interface | Design | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2025-04-12 | 2025-04-12 | 2025-10-12 | FALSE | FALSE | 2025-11-12 | PERERA I A T D it22902702 |  |  | Green | Prepare engagement dataset for ML model training
T1aXk92DkslQp01 | Prepare student behavioural dataset for ML training | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2025-06-12 | 2025-06-12 | 2025-11-12 | FALSE | FALSE | 2025-05-12 | PERERA I A T D it22902702 |  |  | Green | Prepare engagement dataset for ML model training
9HsPp83LksdLp22 | Design chatbot settings panel interface | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2025-06-12 | 2025-06-12 | 2025-10-12 | FALSE | FALSE | 2025-10-12 | NIMANJI D L K it22365750 |  |  | Yellow | Create settings panel layout
T3cKp19HsdfPq22 | Feature engineering for engagement indicators | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2025-06-12 | 2025-06-12 | 2025-12-12 | FALSE | FALSE | 2025-12-12 | PERERA I A T D it22902702 |  |  | Green | Create behavioral engagement features
2RtLp92KlsdQp22 | Design prototype for counterfactual recommendation interface | Design | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2025-07-12 | 2025-07-12 | 2025-12-12 | FALSE | FALSE | 2025-12-12 | RAVISANKA U V P it22354792 |  |  | Yellow | Counterfactual UI design
T4dWp18HdksPp42 | Design prototype for recommendation interface | Design | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2025-08-12 | 2025-08-12 | 2025-12-12 | FALSE | FALSE | 2025-12-12 | DISANAYAKA S T it22370228 |  |  | Yellow | Create recommendation UI prototype
1LmPq82PlsQwP33 | Design document access interface for PDF resources | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2025-09-12 | 2025-09-12 | 13/12/2025 | FALSE | FALSE | 13/12/2025 | NIMANJI D L K it22365750 |  |  | Yellow | PDF access UI design
T5eAq83LmjsPq81 | Define student engagement indicators | Design | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2025-10-12 | 2025-10-12 | 14/12/2025 | FALSE | FALSE | 14/12/2025 | PERERA I A T D it22902702 | 0/3 | Define login metrics;Define activity metrics;Define submission metrics | Pink | Define ML input variables
2PwLp82KlsdPq44 | Design personalized recommendation UI | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2025-12-12 | 2025-12-12 | 16/12/2025 | FALSE | FALSE | 16/12/2025 | NIMANJI D L K it22365750 |  |  | Yellow | Feedback UI design
3RuLp82KlsdQp33 | Develop hybrid ML model (Random Forest + XGBoost + LightGBM) for student risk prediction | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2025-12-12 | 2025-12-12 | 20/12/2025 | FALSE | FALSE | 20/12/2025 | RAVISANKA U V P it22354792 |  |  | Green | Hybrid ML risk model
T6fWl32KdlspZ91 | Implement frontend layout for dashboard | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2025-12-12 | 2025-12-12 | 18/12/2025 | FALSE | FALSE | 18/12/2025 | DISANAYAKA S T it22370228 |  |  | Green | Dashboard UI layout
3AsLp92KlsdQp55 | Design reminder popup interface for notifications | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 15/12/2025 | 15/12/2025 | 20/12/2025 | FALSE | FALSE | 20/12/2025 | NIMANJI D L K it22365750 |  |  | Yellow | Reminder popup UI
T7gXc71PqlsjA11 | Train GRU Autoencoder model | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 15/12/2025 | 15/12/2025 | 2026-05-01 | FALSE | FALSE | 2026-05-01 | PERERA I A T D it22902702 |  |  | Green | Train unsupervised disengagement model
4RvLp82KlsdQp44 | Integrate SHAP explainability layer with trained hybrid model | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 18/12/2025 | 18/12/2025 | 24/12/2025 | FALSE | FALSE | 24/12/2025 | RAVISANKA U V P it22354792 |  |  | Green | SHAP explainability integration
T8hKp73OpdkaL21 | Develop recommendation UI components | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 18/12/2025 | 18/12/2025 | 24/12/2025 | FALSE | FALSE | 24/12/2025 | DISANAYAKA S T it22370228 |  |  | Green | Recommendation UI components
4PwLp92KlsdQp66 | Prepare system architecture diagram for chatbot system | Design | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 18/12/2025 | 18/12/2025 | 23/12/2025 | FALSE | FALSE | 23/12/2025 | NIMANJI D L K it22365750 |  |  | Yellow | System architecture planning
T9iVd61LmpsA31 | Evaluate GRU reconstruction error patterns | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 22/12/2025 | 22/12/2025 | 30/12/2025 | FALSE | FALSE | 30/12/2025 | PERERA I A T D it22902702 |  |  | Green | Evaluate anomaly detection errors
5RwLp92KlsdQp55 | Implement XAI microservice with FastAPI and expose risk explanation endpoints | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 22/12/2025 | 22/12/2025 | 30/12/2025 | FALSE | FALSE | 30/12/2025 | RAVISANKA U V P it22354792 |  |  | Green | XAI FastAPI service
5QwLp82KlsdPq77 | Develop React chatbot interface | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 24/12/2025 | 24/12/2025 | 30/12/2025 | FALSE | FALSE | 30/12/2025 | NIMANJI D L K it22365750 |  |  | Green | Frontend chatbot UI
6LpPw92KlsdPq88 | Implement chat conversation component | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 30/12/2025 | 30/12/2025 | 2026-04-01 | FALSE | FALSE | 2026-04-01 | NIMANJI D L K it22365750 |  |  | Green | Chat conversation UI
6RxLp82KlsdQp66 | Build semester history tracking with Firestore student_acc sub collections | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 30/12/2025 | 30/12/2025 | 2026-05-01 | FALSE | FALSE | 2026-05-01 | RAVISANKA U V P it22354792 |  |  | Green | Firestore semester history
T10jKs41MskqF41 | Define risk thresholds (LOW/NORMAL/HIGH) | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-05-01 | 2026-05-01 | 2026-10-01 | FALSE | FALSE | 2026-10-01 | PERERA I A T D it22902702 |  |  | Green | Risk classification limits
7RyLp82KlsdQp77 | Implement real time What If predictor with live risk bar | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2026-05-01 | 2026-05-01 | 2026-12-01 | FALSE | FALSE | 2026-12-01 | RAVISANKA U V P it22354792 |  |  | Green | Realtime risk predictor
T11kFj20PlmsK11 | Implement workload analysis logic | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2026-07-01 | 2026-07-01 | 2026-12-01 | FALSE | FALSE | 2026-12-01 | DISANAYAKA S T it22370228 |  |  | Green | Workload evaluation logic
8PwLp92KlsdQp10 | Implement chat history management features | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2026-08-01 | 2026-08-01 | 13/01/2026 | FALSE | FALSE | 13/01/2026 | NIMANJI D L K it22365750 | 0/3 | Clear chat;Save conversation;Export conversation | Green | Chat history features
T12lKo11ZmslA22 | Develop RL state and action space design | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-10-01 | 2026-10-01 | 15/01/2026 | FALSE | FALSE | 15/01/2026 | PERERA I A T D it22902702 |  |  | Green | RL state space design
9LpPw82KlsdPq21 | Develop FastAPI backend service for chatbot | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2026-12-01 | 2026-12-01 | 18/01/2026 | FALSE | FALSE | 18/01/2026 | NIMANJI D L K it22365750 |  |  | Green | FastAPI backend
8RzLp82KlsdQp88 | Develop student risk dashboard with SHAP waterfall panel | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2026-12-01 | 2026-12-01 | 18/01/2026 | FALSE | FALSE | 18/01/2026 | RAVISANKA U V P it22354792 |  |  | Green | Explainable risk dashboard
T13mQx91AlpsF32 | Implement overloaded week detection system | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2026-12-01 | 2026-12-01 | 18/01/2026 | FALSE | FALSE | 18/01/2026 | DISANAYAKA S T it22370228 |  |  | Green | Detect overloaded weeks
T14nOp62WqpsB91 | Train reinforcement learning Q learning policy | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 15/01/2026 | 15/01/2026 | 20/01/2026 | FALSE | FALSE | 20/01/2026 | PERERA I A T D it22902702 |  |  | Green | RL training
1PwLp82KlsdPq32 | Implement RAG document retrieval system | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 18/01/2026 | 18/01/2026 | 24/01/2026 | FALSE | FALSE | 24/01/2026 | NIMANJI D L K it22365750 |  |  | Green | RAG retrieval
9RaLp92KlsdQp99 | Implement lecturer dashboard with bulk risk view | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 18/01/2026 | 18/01/2026 | 24/01/2026 | FALSE | FALSE | 24/01/2026 | RAVISANKA U V P it22354792 |  |  | Green | Lecturer dashboard
T15oXk10OqpsQ11 | Integrate subject and internship data sources | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 18/01/2026 | 18/01/2026 | 22/01/2026 | FALSE | FALSE | 22/01/2026 | DISANAYAKA S T it22370228 |  |  | Green | Data integration
T16pFj20LmpsR21 | Implement intervention decision engine | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 20/01/2026 | 20/01/2026 | 25/01/2026 | FALSE | FALSE | 25/01/2026 | PERERA I A T D it22902702 |  |  | Green | RL decision engine
2LpPw92KlsdQp43 | Integrate PDF knowledge base into chatbot system | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 22/01/2026 | 22/01/2026 | 28/01/2026 | FALSE | FALSE | 28/01/2026 | NIMANJI D L K it22365750 |  |  | Green | PDF knowledge base
T17qGh31LmpsP55 | Design intervention strategies | Design | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 22/01/2026 | 22/01/2026 | 27/01/2026 | FALSE | FALSE | 27/01/2026 | PERERA I A T D it22902702 | 0/4 | Soft nudge;Reminder;Peer cheer;Human escalation | Yellow | Intervention strategies
3PwLp92KlsdQp54 | Develop web search fallback mechanism | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 26/01/2026 | 26/01/2026 | 2026-01-02 | FALSE | FALSE | 2026-01-02 | NIMANJI D L K it22365750 |  |  | Green | Web fallback
T19sYk22LmpsF13 | Develop FastAPI ML prediction service | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 27/01/2026 | 27/01/2026 | 2026-02-02 | FALSE | FALSE | 2026-02-02 | PERERA I A T D it22902702 |  |  | Green | ML API
T20tJp01LmpsZ22 | Implement Firebase notification system | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 29/01/2026 | 29/01/2026 | 2026-04-02 | FALSE | FALSE | 2026-04-02 | DISANAYAKA S T it22370228 |  |  | Green | Firebase alerts
11RcLp92KlsdQp21 | Generate and seed 5000 student records with multi semester risk history into Firestore | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 29/01/2026 | 29/01/2026 | 2026-05-02 | FALSE | FALSE | 2026-05-02 | RAVISANKA U V P it22354792 |  |  | Green | Firestore dataset generation
T21uHc09PqslK91 | Integrate ML model with backend API | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-02-02 | 2026-02-02 | 2026-07-02 | FALSE | FALSE | 2026-07-02 | PERERA I A T D it22902702 |  |  | Green | Backend ML integration
5PwLp92KlsdQp76 | Integrate Firebase authentication and Firestore database | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2026-03-02 | 2026-03-02 | 2026-09-02 | FALSE | FALSE | 2026-09-02 | NIMANJI D L K it22365750 |  |  | Green | Firebase integration
T22vQk10LmpsM21 | Connect database with backend API | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2026-04-02 | 2026-04-02 | 2026-10-02 | FALSE | FALSE | 2026-10-02 | DISANAYAKA S T it22370228 |  |  | Green | Database connection
12RdLp82KlsdQp32 | Build one click PDF risk report with SHAP charts | Development | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2026-05-02 | 2026-05-02 | 2026-12-02 | FALSE | FALSE | 2026-12-02 | RAVISANKA U V P it22354792 |  |  | Green | PDF risk report
T23wYl33LpsmD18 | Develop student risk dashboard | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-07-02 | 2026-07-02 | 13/02/2026 | FALSE | FALSE | 13/02/2026 | PERERA I A T D it22902702 |  |  | Green | Risk dashboard
6LpPw92KlsdQp87 | Implement PDF download functionality in chatbot | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2026-08-02 | 2026-08-02 | 14/02/2026 | FALSE | FALSE | 14/02/2026 | NIMANJI D L K it22365750 |  |  | Green | PDF download
T24xFp28MskdQ11 | Develop recommendation dashboard UI | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2026-10-02 | 2026-10-02 | 16/02/2026 | FALSE | FALSE | 16/02/2026 | DISANAYAKA S T it22370228 |  |  | Green | Recommendation UI
13ReLp82KlsdQp43 | Test SHAP explanation accuracy against manual feature analysis | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2026-12-02 | 2026-12-02 | 18/02/2026 | FALSE | FALSE | 18/02/2026 | RAVISANKA U V P it22354792 |  |  | Blue | SHAP testing
7PwLp92KlsdQp98 | Develop voice response system (Text to Speech) | Development | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 2026-12-02 | 2026-12-02 | 18/02/2026 | FALSE | FALSE | 18/02/2026 | NIMANJI D L K it22365750 |  |  | Green | Voice assistant
T25yJk71LmpsS91 | Develop RL decision dashboard | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 13/02/2026 | 13/02/2026 | 18/02/2026 | FALSE | FALSE | 18/02/2026 | PERERA I A T D it22902702 |  |  | Green | RL dashboard
T26zDp72LmpsR77 | Implement UI improvements for chatbot | Development | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 16/02/2026 | 16/02/2026 | 20/02/2026 | FALSE | FALSE | 20/02/2026 | DISANAYAKA S T it22370228 |  |  | Green | Chatbot UI improvements
T27aQp21LskdR88 | Develop Peer Cheer monitoring dashboard | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 18/02/2026 | 18/02/2026 | 22/02/2026 | FALSE | FALSE | 22/02/2026 | PERERA I A T D it22902702 |  |  | Green | Peer support dashboard
14RfLp92KlsdQp54 | Validate risk percentage calculations across thresholds | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 18/02/2026 | 18/02/2026 | 22/02/2026 | FALSE | FALSE | 22/02/2026 | RAVISANKA U V P it22354792 |  |  | Blue | Risk validation testing
8LpPw92KlsdQp19 | Test chatbot response accuracy from RAG system | Testing | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 20/02/2026 | 20/02/2026 | 25/02/2026 | FALSE | FALSE | 25/02/2026 | NIMANJI D L K it22365750 |  |  | Blue | RAG testing
T28bCp10LmpsB29 | Test ML model prediction accuracy | Testing | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 20/02/2026 | 20/02/2026 | 22/02/2026 | FALSE | FALSE | 22/02/2026 | DISANAYAKA S T it22370228 |  |  | Blue | Model testing
T29cEp09LskdF12 | Develop Human Escalation support dashboard | Development | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 22/02/2026 | 22/02/2026 | 26/02/2026 | FALSE | FALSE | 26/02/2026 | PERERA I A T D it22902702 |  |  | Green | Human escalation dashboard
15RgLp92KlsdQp65 | Test real time slider prediction debounce and API handling | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 22/02/2026 | 22/02/2026 | 25/02/2026 | FALSE | FALSE | 25/02/2026 | RAVISANKA U V P it22354792 |  |  | Blue | Realtime predictor testing
T30dGp82LpsmJ81 | Validate study plan generation results | Testing | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 24/02/2026 | 24/02/2026 | 27/02/2026 | FALSE | FALSE | 27/02/2026 | PERERA I A T D it22902702 |  |  | Blue | Recommendation validation
T31eHp62LmpsA01 | Conduct usability testing with students | Testing | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 25/02/2026 | 25/02/2026 | 28/02/2026 | FALSE | FALSE | 28/02/2026 | DISANAYAKA S T it22370228 |  |  | Blue | Usability testing
16RhLp82KlsdQp76 | Verify semester history data loads correctly from Firestore | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 25/02/2026 | 25/02/2026 | 28/02/2026 | FALSE | FALSE | 28/02/2026 | RAVISANKA U V P it22354792 |  |  | Blue | Firestore history testing
9PwLp92KlsdQp20 | Test chatbot web search fallback responses | Testing | Completed | Medium | NIMANJI D L K it22365750 | NIMANJI D L K it22365750 | 26/02/2026 | 26/02/2026 | 2026-03-03 | FALSE | FALSE | 2026-03-03 | NIMANJI D L K it22365750 |  |  | Blue | Web fallback testing
T32fIp10LkpsM18 | Test integration between ML model and backend API | Testing | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 27/02/2026 | 27/02/2026 | 2026-02-03 | FALSE | FALSE | 2026-02-03 | PERERA I A T D it22902702 |  |  | Blue | Integration testing
17RiLp92KlsdQp87 | Test PDF report generation across different risk levels | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 28/02/2026 | 28/02/2026 | 2026-03-03 | FALSE | FALSE | 2026-03-03 | RAVISANKA U V P it22354792 |  |  | Blue | PDF testing
T33gJp82LmpsQ55 | Conduct user testing | Testing | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 28/02/2026 | 28/02/2026 | 2026-03-03 | FALSE | FALSE | 2026-03-03 | DISANAYAKA S T it22370228 |  |  | Blue | UI feedback
T34hKp91LmpsT23 | Identify and fix system bugs during testing | Testing | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-02-03 | 2026-02-03 | 2026-05-03 | FALSE | FALSE | 2026-05-03 | PERERA I A T D it22902702 |  |  | Blue | Debugging
18RjLp92KlsdQp98 | Validate smart alerts trigger correctly at defined thresholds | Testing | Completed | Medium | RAVISANKA U V P it22354792 | RAVISANKA U V P it22354792 | 2026-03-03 | 2026-03-03 | 2026-07-03 | FALSE | FALSE | 2026-07-03 | RAVISANKA U V P it22354792 |  |  | Blue | Alert trigger testing
T35iLp11LmpsG11 | Test Firebase notification delivery | Testing | Completed | Medium | DISANAYAKA S T it22370228 | DISANAYAKA S T it22370228 | 2026-03-03 | 2026-03-03 | 2026-05-03 | FALSE | FALSE | 2026-05-03 | DISANAYAKA S T it22370228 |  |  | Blue | Notification testing
T36jMp11LmpsH21 | Perform system integration testing (frontend backend ML) | Testing | Completed | Medium | PERERA I A T D it22902702 | PERERA I A T D it22902702 | 2026-04-03 | 2026-04-03 | 2026-06-03 | FALSE | FALSE | 2026-06-03 | PERERA I A T D it22902702 |  |  | Blue | System integration